## Model_Summary
Parameter | Value | Description
Total_Blocks | 24 | Total number of blocks to schedule
Block_Types | 3 | Number of different block types (BB, SB, DB)
Total_Stages | 4 | Number of sequential production stages
Total_Machines | 9 | Total number of machines/workstations
Machines_Stage_1 | 2 | Steel cutting machines
Machines_Stage_2 | 3 | Welding stations
Machines_Stage_3 | 3 | Assembly bays (both need cranes)
Machines_Stage_4 | 1 | Finishing stations
Shared_Cranes_Stage_3 | 2 | Number of shared cranes for assembly stage
Min_Processing_Time | 3 | Shortest processing time across all operations
Max_Processing_Time | 14 | Longest processing time across all operations
Min_Setup_Time | 0 | Shortest setup time (same block type)
Max_Setup_Time | 1.5 | Longest setup time (different block types)

## Block_Types
Block_Type | Block_Name | Description | Complexity | Priority | Quantity_Required
BB | Bottom Blocks | Heavy structural blocks forming ship bottom | High | 1 | 8
SB | Side Blocks | Vertical hull sections with curved surfaces | Medium | 2 | 10
DB | Deck Blocks | Horizontal platform structures with equipment foundations | Medium | 3 | 6

## Production_Order
Block_ID | Block_Type | Priority_Weight
BB_01 | BB | 1
BB_02 | BB | 1
BB_03 | BB | 1
BB_04 | BB | 1
BB_05 | BB | 1
BB_06 | BB | 1
BB_07 | BB | 1
BB_08 | BB | 1
SB_01 | SB | 2
SB_02 | SB | 2
SB_03 | SB | 2
SB_04 | SB | 2
SB_05 | SB | 2
SB_06 | SB | 2
SB_07 | SB | 2
SB_08 | SB | 2
SB_09 | SB | 2
SB_10 | SB | 2
DB_01 | DB | 3
DB_02 | DB | 3
DB_03 | DB | 3
DB_04 | DB | 3
DB_05 | DB | 3
DB_06 | DB | 3

## Processing_Times
Block_Type | S1_M1 | S1_M2 | S2_M1 | S2_M2 | S2_M3 | S3_M1 | S3_M2 | S3_M3 | S4_M1
BB | 6 | 7 | 8 | 9 | 7 | 12 | 14 | 13 | 4
SB | 4 | 5 | 6 | 7 | 5 | 8 | 9 | 8 | 3
DB | 5 | 6 | 7 | 8 | 6 | 10 | 11 | 11 | 3

## Machine_Information
Stage | Machine_ID | Machine_Name | Stage_Name | Requires_Crane | Description
1 | S1_M1 | CNC Plasma Cutter A | Steel Cutting | FALSE | High-precision steel cutting
1 | S1_M2 | CNC Plasma Cutter B | Steel Cutting | FALSE | Standard steel cutting
2 | S2_M1 | Welding Station A | Welding | FALSE | Primary welding operations
2 | S2_M2 | Welding Station B | Welding | FALSE | Secondary welding operations
2 | S2_M3 | Welding Station C | Welding | FALSE | Specialized welding
3 | S3_M1 | Assembly Bay A | Assembly | TRUE | Heavy block assembly (needs crane)
3 | S3_M2 | Assembly Bay B | Assembly | TRUE | Standard block assembly (needs crane)
3 | S3_M3 | Assembly Bay 3 | Assembly | TRUE | Standard block assembly (needs crane)
4 | S4_M1 | Finishing Station A | Finishing | FALSE | Surface finishing and final preparation

## Setup_Times_Matrix
From_Block_Type | To_BB | To_SB | To_DB
BB | 0 | 1.5 | 1
SB | 1.5 | 0 | 1
DB | 1 | 1 | 0

## Setup_Times_Detail
From_Block_Type | To_Block_Type | Setup_Time_Hours
BB | BB | 0
BB | SB | 1.5
BB | DB | 1
SB | BB | 1.5
SB | SB | 0
SB | DB | 1
DB | BB | 1
DB | SB | 1
DB | DB | 0

## Stage_Machine_Mapping
Stage | Machine_ID | Machine_Name | Requires_Crane
1 | S1_M1 | CNC Plasma Cutter A | FALSE
1 | S1_M2 | CNC Plasma Cutter B | FALSE
2 | S2_M1 | Welding Station A | FALSE
2 | S2_M2 | Welding Station B | FALSE
2 | S2_M3 | Welding Station C | FALSE
3 | S3_M1 | Assembly Bay A | TRUE
3 | S3_M2 | Assembly Bay B | TRUE
3 | S3_M3 | Assembly Bay C | TRUE
4 | S4_M1 | Finishing Station A | FALSE

## Resource_Constraints
Resource_Type | Stage | Capacity | Required_By_Machines | Description
Crane | 3 | 2 | S3_M1, S3_M2, S3_M3 | Overhead cranes required for assembly operations

## System_Parameters
Parameter | Value | Description
Working_Hours_Per_Day | 16 | Total operating hours per day (2 shifts)
Number_of_Shifts | 2 | Number of shifts per day
Total_Blocks_To_Schedule | 24 | Total number of blocks in production order
Number_of_Stages | 4 | Number of sequential production stages
Number_of_Machines | 9 | Total number of machines/workstations
Number_of_Cranes_Stage3 | 2 | Number of shared cranes in Assembly stage
Project_Name | Simplified Bulk Carrier Block Production | Project identification